The rise of food costs in America

Brittney N. Orais-Bonheimer

Western Governors University

Table of Contents

A. Proposal Overview	3

A.1 Research Question or Organizational Need	3

A.2 Context and Background	3

A.3 and A3A Summary of Published Works and Their Relation to the Project	3

A.5 Benefits and Support of Decision-Making Process	6

B. Data Analytics Project Plan	6

B.1 Goals, Objectives, and Deliverables	6

B.2 Scope of Project	7

B.2.A Included in Project Scope	7

B.2.B Not included in Project Scope	7

B.3 Standard Methodology	7

B.4 Timeline and Milestones	8

B.5 Resources and Costs	9

B.6 Criteria for Success	10

C. Design of Data Analytics Solution	10

C.1 Hypothesis	10

C.2 and C.2.A Analytical Method	10

C.3 Tools and Environments	10

C.4 and C.4.A Methods and Metrics to Evaluate Statistical Significance	11

I will be finding the p-value of the data to verify statistical significance. This is the common way to verify the ARIMA model statistical significance.	11

C.5 Practical Significance	11

C.6 Visual Communication	11

D. Description of Dataset	11

D.1 Source of Data	11

D.2 Appropriateness of Dataset	11

D.3 Data Collection Methods	12

The data was downloaded from the USDA.gov website as an Excel file. It was then converted into two CSV files to be uploaded onto jupyter notebooks.	12

D.4 Observations on Quality and Completeness of Data	12

D.5 and D.5.A Data Governance, Privacy, Security, Ethical, Legal, and Regulatory Compliances	12

References	13

# A. Proposal Overview

## A.1 Research Question or Organizational Need

If the cost of food continues to rise at the same rate, how much will food cost 5 years from now? Since our organization is a nonprofit working towards ending food insecurity for families, we need to be able to predict how much we will need to grow in the next 5 years to keep up with needs as well as gain more donor support.

## A.2 Context and Background

The (Fictional) non-profit Feeding Families is looking to expand its services in the next 5 years. Since the pandemic, food inflation has been rising and continues to do so at an alarming rate. This means that in just a few years, food costs could become unaffordable for families that may not be struggling at the moment. This means nonprofits like Feeding Families will have to grow as well. Feeding Families wants to show potential donors how important their nonprofit is to American Families and how the need for food security will grow in the next few years.

## A.3 and A3A Summary of Published Works and Their Relation to the Project

Adjemian, M. K., Arita, S., Meyer, S., & Salin, D. Factors affecting recent food price inflation in the United States. Applied Economic Perspectives and Policy. https://doi.org/10.1002/aepp.13378

This article attempts to better understand the factors causing accelerated food inflation in America by using data modeling methods. Food prices have been rising due to multiple factors such as the war in Ukraine, shipping costs, and increased production costs. Supply chain disruptions caused by the pandemic and an imbalance of supply and demand have been major drivers of inflation. The excessive spending by the federal government and fiscal stimulus are also contributing to inflation by perpetuating the supply and demand imbalance. The year-over-year food price inflation in 2022 exceeded 10%. (Adjemian et al.)  These high increases have not been seen since the 1970’s and early 1980’s. Since inflation caused by supply chain disruptions usually flatten out by themselves, demand can be a top contributor to sustained inflation rate acceleration.

This article discusses the factors contributing to the increase in food inflation compared to general inflation. Understanding these reasons is critical when predicting whether this increase is temporary or if it will persist at a similar rate. Since this is a global issue with many influencing factors, it will likely continue to rise in the foreseeable future, rather than stabilize.

Okafor, C., & Shaibu, I. (n.d.). Application of Arima models to Nigerian inflation dynamics - core. https://core.ac.uk/download/pdf/234629451.pdf

This academic article was published by The International Institute for Science,

Technology and Education. This study aimed to develop an ARIMA model for Nigerian inflation and assess its forecasting performance from 1981 to 2010. The study identified ARIMA as the most suitable model for short-term inflation forecasting based on diagnostic and selection criteria. The ARIMA model successfully tracked actual inflation during the sample period.

ARIMA methodology was employed by Stockton & Glassman in 1987 to model inflation in the United States. Their analysis suggested that ARIMA models are theoretically justified and can exhibit resilience when compared to alternative multivariate modeling approaches. (Okafor & Shaibu)

This study is important because it shows an example of the ARIMA model used to predict inflation accurately.

Kontopoulou, V. I., Panagopoulos, A. D., Kakkos, I., & Matsopoulos, G. K. (2023). A Review of ARIMA vs. Machine Learning Approaches for Time Series Forecasting in Data-Driven Networks. Future Internet, 15(8), 255. MDPI AG. Retrieved from http://dx.doi.org/10.3390/fi15080255

This article discusses the use of ARIMA models in time series data vs. newer machine learning approaches developed with AI techniques. The study compares the accuracy of ARIMA modeling to machine learning using multiple time series data sets. Since machine and deep learning are difficult to verify, this study was used to distinguish their accuracy compared to traditional autoregressive methods. ARIMA models are used in statistics and econometrics to analyze time series data. They are a generalization of autoregressive moving average models and are fitted to data to understand or predict future points in a series. The purpose of AR, MA, and I components in ARIMA models is to fit the model to the data. The observations show the most accurate modeling techniques are dependent on the data that is being forecasted.

This article is important to the project because it compares ARIMA modeling to machine learning and deep learning. It concludes that ARIMA modeling continues to be relevant for forecasting data. This article also explained in detail about ARIMA modeling

A.4 Summary of Data Analytics Solution

I will be analyzing weekly retail food sales data from the past to effectively predict the costs of food in the future. I will use the ARIMA analytic model on the data which will predict future costs based on past data. This data will demonstrate the growing need for our services as more and more Americans face food insecurity due to accelerated inflation rates.

## A.5 Benefits and Support of Decision-Making Process

The benefit of this data analysis will be that will emphasize the rapidly rising food cost in the United States, thereby providing valuable insights. As a non-profit that helps families going through food insecurity, the need for our organization will continue to grow as well as our need for funding. With the information gained from this analysis, our organization hopes to gain more funding so we can expand our services to more people in the community in the next 5 years based on the forecasted need for more and more families.

# B. Data Analytics Project Plan

In this part, you will discuss the design details of your capstone data analytics solution.

## B.1 Goals, Objectives, and Deliverables

- Goal: This project aims to create a prediction model that will accurately forecast future food costs. This will be used to show stakeholders the growing need for expanded services and funding for the nonprofit.

- Objective 1.1: Determine what the cost of food will be in 5 years based on historical data using the ARIMA model.

    - Deliverable 1.1.1: Provide the average percentage change of food costs in 5 years as determined by ARIMA modeling and current weekly retail food sales data from the USDA.gov website. ARIMA modeling forecasts future data points on time series data like the weekly retail food data. Through this process, we will be able to forecast inflation rates based on the current accelerated rise in food costs.

    - Deliverable 1.1.2: Provide examples of the cost of different staple food items in 5 years such as eggs and poultry using the ARIMA model. This will be achieved by analyzing the data to find food items that have the largest rate of inflation from the weekly retail food sales data we will download from the USDA.gov website. This data includes data broken down by food category and subcategory. A scatterplot will be used to find subcategories that have high inflation rates currently. Then the ARIMA model will be used to forecast these food costs in 5 years. This data will be used to provide perspective on what food prices are predicted to look like in 5 years.

## B.2 Scope of Project

### B.2.A Included in Project Scope

This project's scope is to create a predictive model using Python in Jupyter Notebook. This model will be an ARIMA model that will forecast future food costs based on current weekly retail food sales data from the USDA.gov website. The predictive model will forecast the average percentage change in the cost of food 5 years from now. This model will be used to forecast the average cost and percentage change in the cost per unit of selected examples of food subcategories using the current data from the USDA.gov website. The predictions will include scatter plots of the current data showing the current rate of inflation for all food as well as food subcategories. The main constraint is the data is weekly retail food sales as a total amount and total unit amount. Although the data is divided into categories and subcategories, it is not possible to get detailed information on very specific food items. The data is also national, not local.

### B.2.B Not included in Project Scope

This project will not include data predictions for any other timeframe other than 5 years. It will not include the average food cost per unit based on food categories. It will also not include the average price per unit on current food costs.

## B.3 Standard Methodology

I will be using the waterfall methodology for this project.

- Requirements – The requirements will be needed upfront for this project. This includes reviewing the scope of the project and discussing the assumptions, success metrics, and timeline with stakeholders. I will be creating a project plan including all of the people who will be involved in the project and discussing everyone’s expectations of the project.

- Design – Determine the data and tools needed for this project as well as deciding which analysis methods will be used. Design the timeline and deliverables. The data that will be used is the weekly retail sales of food data from the USDA.gov website. This data will be analyzed with Python in Jupyter Notebook to find an average food cost per unit. This will then be used to create a predictive model to forecast future food costs based on the current rate of inflation. Since this is time series data, I will be using the ARIMA model to forecast future data points.

- Implementation – Collecting the data needed and then using data analysis tools to forecast future data points. Will create and implement models to make accurate predictions and document each step of the process. I will download the data from the USDA.gov website. This data was in an Excel file. The data will be reviewed in Excel and then uploaded to Jupyter Notebook for further analysis using Python. Once the data is analyzed, I will create the ARIMA model and create data plots with the forecasted food costs. This will then be used to find the average percentage change.

- Verification – Verifying all code is working correctly and creating data visualizations that portray data point predictions accurately. I will carefully review the data visualizations as well as use the dickey-fuller test to verify if the data is non-stationary. The auto ARIMA model fits the data automatically to ensure accuracy when forecasting data points. Once the coding is complete, I will verify all code is working correctly and the data visualizations look accurate.

- Maintenance –  Since this is going to be used once, no maintenance is needed on this project. We could potentially use the same model for future forecasting so I will be saving the code used to make recreating the project in the future quick and easy.

## B.4 Timeline and Milestones

| Milestone or deliverable | Duration (hours or days) | Projected start date | Anticipated end date |
| --- | --- | --- | --- |
| Collecting the data needed to the analysis | 1 hour | 11/09/2023 | 11/09/2023 |
| Cleaning the data if needed | 2 hours | 11/09/2023 | 11/09/2023 |
| Analyzing the data | 2 hours | 11/09/2023 | 11/09/2023 |
| Using various data visualizations to further analyze the data | 2 hours | 11/09/2023 | 11/09/2023 |
| Create the ARIMA model and use to forecast food costs in 5 years | 4 hours | 11/09/2023 | 11/10/2023 |
| Calculate the average percentage change in food costs in 5 years | 1 hour | 11/10/2023 | 11/10/2023 |
| Create the ARIMA model and use to forecast specific food costs in 5 years (eggs, poultry, ect) to use as examples. | 3 hours | 11/10/2023 | 11/10/2023 |
| Calculate the percentage change in example food costs in 5 years | 1 hour | 11/10/2023 | 11/10/2023 |
| Create notes in Jupyter notebook using markdown language explaining every step. | 4 hours | 11/10/2023 | 11/11/2023 |
| Review results with stake holders | 1 hour | 11/12/2023 | 11/12/2023 |

## B.5 Resources and Costs

- Data from the USDA.gov website: No cost

- Microsoft Excel: No cost

- Python using Jupyter Notebooks: No cost

- 21 hours of work: $1050 (21 hours at $50 per hour)

The resources for this project will mainly be the data, Excel, and Python using Jupyter Notebook for the analysis, as well as my time which is outlined in the timeline as projected to be around 21 hours at my pay of $50 an hour. The only cost is the time spent on the project.

## B.6 Criteria for Success

The criteria for success on this project will be measured in multiple ways. This project will be successful if we can achieve results within 3-5 business days and with one employee working on the project to save on expenses. This will be measured by the hours I spend on the project. If this project is a success, we will be able to accurately forecast data points using the ARIMA data model and effectively use it to better understand how much food costs will grow in 5 years. This will be measured by accurately forecasting the data points needed to find the average percentage change in food costs in 5 years as well as the average unit cost and percentage change for selected food subcategories. This will help confirm the need to expand our nonprofit and request more funding.

# C. Design of Data Analytics Solution

## C.1 Hypothesis

If inflation on food prices continues to rise at the same rate, then many Americans will find it difficult to feed their families because the cost of food will become unaffordable within the next 5 years.

Using ARIMA modeling I will predict the cost of food in the future based on the rapidly rising inflation rate.

## C.2 and C.2.A Analytical Method

I will be using the Autoregressive integrated moving average (ARIMA) data model to predict future data points using historical data. The ARIMA model is a type of regression model that uses time series data to forecast future data points.

C.2.A Justification of analytical method

ARIMA is a generalization of autoregressive moving average models and is fitted to data to understand or predict future points in a series. This model is the most appropriate analytical method since it can be used with time series data like the weekly retail food cost data we will be using.  This model has been proven effective in forecasting inflation rates in many countries around the world. The data we are using will be fitted to the ARIMA model which will then be able to predict future data points based on the inflation rate of the data we will provide.

## C.3 Tools and Environments

The project will be done using Excel and Python in Jupyter Notebook. The Python packages that will be used include pandas, numpy, matplotlib, sklearn, DateTime, and pmdarima. The data sets used were from the USDA.gov website and were downloaded in Excel files. I chose this data because it is public government data that provides the weekly retail sales of food from 2019-2023. This will be used to forecast food costs in 5 years. Python in Jupyter Notebooks and all of the listed Python packages will provide an environment to properly analyze and build our ARIMA model for forecasting.  Excel will be used when the data is first downloaded before it is uploaded into Jupyter Notebook.

## C.4 and C.4.A Methods and Metrics to Evaluate Statistical Significance

Since the data I will be using is time series data, I will be using the Autoregressive integrated moving average (ARIMA) data model to predict future data points using historical data. The ARIMA model is a type of regression model that uses time series data to forecast future data points. With the ARIMA model, data is first plotted and analyzed. Data used in ARIMA modeling must be stationary, which means the data is consistent over time. If the data is not consistent, it is nonstationary and will need to be transformed to become stationary. Using the Dickey-Fuller (ADF) test, we can determine if the data is nonstationary by looking at its p-value. If the data is nonstationary, we can use a process called differencing to remove changes in the time series data and make it stationary. We can then perform the ADF test again to verify the data have been transformed properly.

C.4.A Justification of methods and metrics

The data we are using is time series data. This means that it is a set of data points over a period of time. Since most methods are used to correlate two different variables, they can be difficult to use with time series data. When working with time series data, the best model to use for predictions is the ARIMA model. With ARIMA modeling, we should use the Dickey-Fuller (ADF) test. This technique confirms whether the data is stationary or not. If time series data is stationary, it means that the mean does not vary in time. Most time series data changes through time so it is nonstationary and will need to be transformed using various methods such as differencing to become stationary. Once this process is done, the ADF test will show a p-value proving statistical significance.

## C.5 Practical Significance

The practical significance of this project will be if the ARIMA model predicts a large increase in the cost of food in the 5-year time frame. I large increase would be anything higher than 15% as this is what our current organization could manage with our current infrastructure and funding.  If it is higher than 15%, it will be significant for our organization because it will mean we will need to expand to continue to support our community. If food inflation continues to accelerate and rises over the general inflation rate, many families may be faced with food insecurity and need our services.

## C.6 Visual Communication

Using Python in Jupyter Notebook, I will be creating multiple data visualizations throughout the project. I will first create a scatterplot showing all of the weekly average dollars per unit from 2019-2023. This will be used to analyze the inflation rate as well as check for outliers and other anomalies. I will then make a scatterplot for the subcategories to analyze which subcategories have the higher inflation rates over the timeframe. Once we start the ARIMA modeling process, a plot graph will be made, then graphs to see the Autocorrelation when verifying if the data is stationary. There will be a plot graph that uses differencing on the data, then graphs showing the forecasted food costs we created with the ARIMA model. This will be done for the total average food costs as well as a few selected subcategory food costs to give perspective on what the inflation rise will look like on common food costs.

# D. Description of Dataset

## D.1 Source of Data

I will be gathering data from the USDA.gov website: https://www.ers.usda.gov/data-products/weekly-retail-food-sales/ This website has two datasets, one with weekly retail food sales for the country and one includes subcategories of food items.

## D.2 Appropriateness of Dataset

The data from the USDA.gov website is public information from the government so it is a trusted source and easy to collect. These datasets are appropriate for this project because they contain the weekly retail food sales for the nation, which will be used to accurately fit the ARIMA model to forecast future food costs based on the data provided here. The datasets will be downloaded from the USDA.gov website as an Excel file with two tabs. One has the weekly retail food sales totals for the country. This includes columns with the date reported, total dollars spent, and total unit sales. Multiple other columns will not be needed for this analysis. This information will be used to produce an average dollar amount per unit per week which will be used to fit the ARIMA model and forecast future data points. I will use this data to create scatterplots to analyze the inflation rate from 2019 to 2023. The other tab has the same columns but also includes columns for the food category and subcategory. This will be used in a similar way to produce an average cost per unit for different subcategories of food items such as eggs and poultry. I will use this data to create scatterplots and for the ARIMA model so I will have specific food cost examples to show shareholders and have a better perspective of what common food items are predicted to cost in 5 years. The disadvantage of these datasets is that they are weekly totals in dollars and total units sold. This means that we will have to find the average cost per unit for our analysis. The data is also only reported from 2019-2023 so we are unable to calculate the average percentage change in 5 years based on this data to compare to the forecasted percentage change in 5 years.

## D.3 Data Collection Methods

## The data I am using is the National Weekly retail food sales from the USDA.gov website. This data is public and from the government so it is trusted to be accurate. The data will be downloaded as an Excel file from the USDA.gov website. Since the data is already in an Excel spreadsheet, it will need very little cleaning and formatting. I will then open the file in Excel, and review both the ‘National Total’ and ‘National by Subcategory’ tabs. I will then check both datasets for any formatting issues or rows that need to be deleted before I can upload them into Jupyter Notebooks. I will save the Excel file and upload it to jupyter notebooks for data analysis. The data is also only reported from 2019-2023 so we are unable to calculate the average percentage change in 5 years based on this data to compare to the forecasted percentage change in 5 years.

## D.4 Observations on Quality and Completeness of Data

The data was clean and complete when downloaded, there are a few formatting issues that will need to be fixed before uploading to Jupyter notebooks. The data was downloaded as an Excel file from the USDA.gov website. I then opened the file in Excel, there were two tabs I was interested in, ‘National Total’ and ‘National by Subcategory’. I reviewed both tabs, there was a header in both that needed to be deleted from the first row. That way, the column names would upload correctly in the data frame. I formatted the ‘Date’ column as date and the ‘Dollars’ and ‘Unit sales’ columns as numbers in both tabs to ensure the correct data types when uploading to the data frame. Lastly, there were multiple rows at the end of each tab that explained certain variables. Since these rows would create an issue when analyzing the data, they were deleted as well. I saved the Excel file, then uploaded it to jupyter notebooks.

## D.5 and D.5.A Data Governance, Privacy, Security, Ethical, Legal, and Regulatory Compliances

Since this project was going to be seen by many different stakeholders in our organization, I wanted to use data that was public so that privacy and security would not be a big concern. Data that comes from government websites such as USDA.gov are publically accessible and do not contain sensitive information.

- Data governance –I will be the only person working on this project. Once the data is downloaded from the USDA.gov website, I will ensure that the data is cleaned and that quality and completeness are maintained throughout the data analysis process. I will document the process as well in Jupyter Notebooks using markdown language to ensure the analysis can be duplicated if needed.

- Privacy – The data should not contain any information that is not public. I will carefully review both datasets to confirm that the information does not contain any sensitive information.

- Security – The only security concern would be to ensure the data integrity. The data files will be kept in a secure file that only I will have access to.

- Ethical, legal, and regulatory compliance considerations – No considerations were needed since this data is public and does not include any sensitive information.

# References

Kontopoulou, V. I., Panagopoulos, A. D., Kakkos, I., & Matsopoulos, G. K. (2023). A Review of ARIMA vs. Machine Learning Approaches for Time Series Forecasting in Data-Driven Networks. Future Internet, 15(8), 255. MDPI AG. Retrieved from http://dx.doi.org/10.3390/fi15080255

Patton, M. (2023, September 3). Food prices outpace general inflation: Here’s what you need to know. Forbes. https://www.forbes.com/sites/mikepatton/2023/08/30/food-prices-outpace-general-inflation-heres-what-you-need-to-know/?sh=4d05d3096fbd                                                                                                                              United States Food InflationSeptember 2023 data - 1914-2022 historical. United States Food Inflation - September 2023 Data - 1914-2022 Historical. (n.d.). https://tradingeconomics.com/united-states/food-inflation                                                                                                                                                                           Hannon, P. (2023, August 4). Inflation is cooling. food inflation could get worse. The Wall Street Journal. https://www.wsj.com/articles/inflation-is-cooling-food-inflation-could-get-worse-bb373e06                                                                                                                                                                         urdue University. (n.d.). Retrieved from APA Formatting and Style Guide (7th Edition) - Purdue OWL: https://owl.purdue.edu/owl/research_and_citation/apa_style/apa_formatting_and_style_guide/index.html

Scribbr. (2022, December 21). Free Citation Generator. Retrieved from Scribbr: https://www.scribbr.com/citation/generator/

Smith, J. (2023). A Generic Journal Article Example. Generic Journal, 50-62.

Okafor, C., & Shaibu, I. (n.d.). Application of Arima models to Nigerian inflation dynamics - core. https://core.ac.uk/download/pdf/234629451.pdf

Wikipedia contributors. (2023, October 9). Autoregressive integrated moving average. In Wikipedia, The Free Encyclopedia. Retrieved 14:30, October 29, 2023, from https://en.wikipedia.org/w/index.php?title=Autoregressive_integrated_moving_average&oldid=1179339959

Adjemian, M. K., Arita, S., Meyer, S., & Salin, D. Factors affecting recent food price inflation in the United States. Applied Economic Perspectives and Policy. https://doi.org/10.1002/aepp.13378